## Dashboard
[ Production by Plant ] | [ Delay Pie Chart ]
[ Efficiency Chart ] | [ Key Numbers ]
📦 Total Orders: 20
⏱️ Delayed Orders: 8
📈 Avg Efficiency: 92%

## pivot-table
Row Labels | Sum of Produced_Qty | Sum of Planned_Qty
A | 6220 | 6720
B | 5820 | 6090
C | 5100 | 5360
Grand Total | 17140 | 18170
Row Labels | Sum of Production Efficiency
Steel A | -170
Steel B | -160
Steel C | -530
Steel D | -170
Grand Total | -1030
Row Labels | Sum of Order_ID
0 | 444
1 | 771
2 | 777
3 | 218
Grand Total | 2210

## production-data
Order_ID | Material | Planned_Qty | Produced_Qty | Delay_Days | Plant | Production Efficiency | Delay status | total order
101 | Steel A | 1000 | 950 | 2 | A | -50 | Delayed | 20
102 | Steel B | 800 | 800 | 0 | B | 0 | ON TIME
103 | Steel C | 1200 | 1000 | 3 | A | -200 | Delayed
104 | Steel D | 600 | 580 | 1 | C | -20 | Delayed
105 | Steel A | 900 | 870 | 1 | B | -30 | Delayed
106 | Steel B | 750 | 700 | 2 | A | -50 | Delayed
107 | Steel C | 1100 | 1050 | 1 | C | -50 | Delayed
108 | Steel D | 650 | 600 | 2 | B | -50 | Delayed
109 | Steel A | 1000 | 980 | 0 | A | -20 | ON TIME
110 | Steel B | 850 | 800 | 1 | C | -50 | Delayed
111 | Steel C | 1300 | 1200 | 2 | B | -100 | Delayed
112 | Steel D | 700 | 650 | 2 | A | -50 | Delayed
113 | Steel A | 950 | 900 | 1 | C | -50 | Delayed
114 | Steel B | 780 | 750 | 1 | B | -30 | Delayed
115 | Steel C | 1250 | 1150 | 3 | A | -100 | Delayed
116 | Steel D | 680 | 670 | 0 | C | -10 | ON TIME
117 | Steel A | 1020 | 1000 | 0 | B | -20 | ON TIME
118 | Steel B | 820 | 790 | 1 | A | -30 | Delayed
119 | Steel C | 1180 | 1100 | 2 | C | -80 | Delayed
120 | Steel D | 640 | 600 | 2 | B | -40 | Delayed

## Inventory_Data
Material | Stock | Min_Stock | Max_Stock
Steel A | 500 | 300 | 1000
Steel B | 200 | 250 | 800
Steel C | 900 | 400 | 1200
Steel D | 300 | 200 | 700